## Project Plan for Reminder App
Message Slips App for Websmith Group
Target Platform: Windows, Mac OS X
Jason Dang
0%
% Complete | Item | Phase | Task | Lead | Supporting | Starting Date | Ending (EDC) | Dependency
| 1.1 | Back-end (SQL) | Database Development | Jason | Mark | 2015-05-18 | 2015-05-19 | Needed before Access Control
| 1.2 | Back-end (SQL) | Adding User | Jason | Mark | 2015-05-19 | 7/515 | Needed before Access Control
| 1.3 | Back-end (SQL) | Storing/Updating User's Info | Jason | Mark | 2015-05-29 | 2015-07-05 | Needed when Reminder Functionality is in progress
| 2.1 | Front-end (Web Interface) | Overall Design/Page Layout | Jason | Mark | 2015-05-13 | 2015-05-15 | Initial Step of the Project
| 2.2 | Front-end (Web Interface) | Access Control (Login/Admin Access) | Jason | Mark, Nate | 2015-05-15 | 2015-05-26 | Required Login Page
| 2.3 | Front-end (Web Interface) | Dashboard Design (Homepage) | Jason | Mark, Nate, Rachel | 2015-05-27 | 2015-05-28 | N/A
| 2.4 | Front-end (Web Interface) | Create Reminder Funtionality | Jason | Mark, Nate | 2015-05-29 | 2015-07-05 | Database
| 2.5 | Front-end (Web Interface) | Email Functionality | Jason | Mark, Nate | 2015-06-12 | 2015-06-18 | Database/Email Access
| 2.6 | Front-end (Web Interface) | Map API/Map Integration | Jason | Mark, Nate | 2015-06-19 | 2015-06-25 | N/A
| 2.7 | Front-end (Web Interface) | Delete/Update Reminder | Jason | Mark, Nate | 2015-06-26 | 2015-07-05 | Database/Create Reminder
| 2.8 | Front-end (Web Interface) | Adding Users | Jason | Mark, Nate | 2015-07-03 | 2015-07-06 | Database
| 3.1 | Testing | Access Control (Login) | Jason | Mark, Nate, Rachel | 2015-05-25 | 2015-05-26 | Completion of Access Control Funtionality
| 3.3 | Testing | Reminder Funtionality | Jason | Mark, Nate, Rachel | 2015-07-01 | 2015-07-03 | Completion of Reminder Functionality
| 3.4 | Testing | User Funtionality | Jason | Mark, Nate, Rachel | 2015-07-06 | 2015-07-06 | Completion of Database Development
| 4.1 | Demo | Web App Demo (to Rachel) | Jason |  | 2015-07-07 | 2015-07-07 | Full Funtionality App
| 4.2 | Beta Test | Beta Test for End-User | Jason |  | 2015-07-09 | 2015-07-09 | Full Funtionality App